Job Ref No: ETD332

Date

OCU REF:   LOT1 EDT332  JG/PM initials

Dear Business Owners/Residents,

RE:  SSE - New Power related electricity planned connection works taking place between The Holiday Inn Express, Wendlebury Road and Bicester Village.

We are writing to inform you of planned essential electricity connection works scheduled to take place from 25th March 2026 to 22nd June 2026.

The works will involve excavating joint bays and trench operations within the footway, cycleway, and carriageway.

The works will be undertaken by OCU Group on behalf of Scottish and Southern Electricity Networks.

To ensure the safety of pedestrians, road users and our work force at all times traffic management will be in operational and in place throughout the duration of the project.

Please note the planned work will be carried out in phases as detailed below.

Phase 1 - A Full Road closure on Wendlebury Road
(From the roundabout at Charles Shouler Way to the section heading from Green Lane to the A41).
Dates: 30th March 2026 to 1st May 2026.

Phase 2 - Multi-way Traffic Lights situated on Wendlebury Road
(From the roundabout at Charles Shouler Way to Bicester Avenue Home & Garden Centre).
Dates: 14th April 2026 to 22nd June 2026.

Phase 3 - Multi-way Traffic Lights situated on Charles Shouler Way
(From the Charles Shouler Way/Wendlebury Road roundabout to the footpath entrance adjacent to the Holiday Inn Express, Bicester).
Dates: 4th April 2026 to 9th June 2026.

Phase 4 - Footpath Works
(Footpath adjacent to Holiday Inn Express to bus stop on A41.  Please be advised no inconvenience to the public).
Dates: 19th April 2026 to 29th April 2026.

Phase 5 – Lane Closures on the A41
(Between the bus stop at Vendee Drive and the entrance into Bicester Village).
Dates: 18th May 2026 to 22nd June 2026.

Please be advised all the above planned works are weather permitting.

We sincerely apologise for any inconvenience the works may cause and appreciate your understanding and cooperation throughout.

Should you have any questions or concerns, please do not hesitate to contact us on:

OCU Customer Services:  0333 200 0011, quoting reference LOT1/ EDT332.

Yours faithfully,

OCU Customer services

Email: NOC_General_Enquiries@ocugroup.com

OCU Project Contact email:  Johnny.Galbraith@ocugroup.com